## Dashboard
Task Tracker Dashboard
[8 empty] | Last Update, | 2025-12-24 | 2025-12-24
|  |  | Group Task 1 | Who's on it | Work Required | Tasks | Deadline | % Completed | Work Left | Status
|  |  | Task 1-1 | Jameel | 1 | Update the costing sheet both columns [ Supply quoted ¦¦ PS quoted ] with either [ Yes ¦¦ Estimated ¦¦ AT&S | 2024-06-26 | 100% | 0 | Completed
|  |  | Task 1-2 | Rami | 1 | AT&S to submit MIRs for 3 different vendors | 2024-07-01 | 10% | 0.9 | Late
|  |  | Task 1-3 | Ahmed | 2 | AT&S to provide KDOCs with the selected [ Concrete Factory , Third Party , Soil Test Lab ] | 2024-07-01 | 0% | 2 | Late
|  |  | Task 1-4 | Ammar | 3 | Costing Sheet update for the VENDORs & Submission Status | 2024-07-01 | 50% | 1.5 | Late
|  |  | Task 1-5 | Bdoor | 1 | Office Land Rent | 2024-07-01 | 50% | 0.5 | Late
Today |  | 2025-12-24 | Group Task 2 | Who's on it | Work Required | Tasks | Deadline | % Completed | Work Left | Status
Red Flag Days |  | 5 | Task 2-1 | Ahmed | 2 | Raise Request to SWCC for Work Permit for 7 sites , Resources & Machinery Sheet should be delivered ¦¦ Target Start Date is July 14th | 2024-07-01 | 0% | 2 | Late
Red Flag Date |  | 2025-12-29 | Task 2-2 | Ammar | 3 | AT&S to submit the method statement for Project Implementation | 2024-07-01 | 0% | 3 | Late
Deadline |  | 2024-07-01 | Task 2-3 | Nazim | 1 | AT&S to submit the Project Time Schedule Base Line | 2024-07-01 | 20% | 0.8 | Late
|  |  | Task 2-4 | Ammar | 3 | AT&S to submit a TQ regarding the Project Payment Terms | 2024-07-01 | 0% | 3 | Late

## Resourcing
Resource | #Tasks | Total Work In Days | Done | Left To Do
Messawei | 0 | 0 | 0 | 0
Jameel | 1 | 1 | 1 | 0
Bdoor | 1 | 1 | 0.5 | 0.5
Abu Saleh | 0 | 0 | 0 | 0
Ahmed | 2 | 4 | 0 | 4
Ammar | 3 | 9 | 1.5 | 7.5
Nazim | 1 | 1 | 0.2 | 0.8
|  | 0 | 0 | 0
Rami | 1 | 1 | 0.1 | 0.9
Yehia | 0 | 0 | 0 | 0
|  | 0 | 0 | 0
|  | 0 | 0 | 0
|  | 0 | 0 | 0
|  | 0 | 0 | 0
|  | 0 | 0 | 0
|  | 0 | 0 | 0
|  | 0 | 0 | 0
Total | 9 | 17 | 3.3 | 13.7

## Comments
Resource | Comments
Messawei

## Calculations
Calculation
Not Started | 4
In Progress | 4
Completed | 1
On Track | 0
Late | 0
Red | 0